## UVA BME Masters 19-20
At Risk | Task Name | Status | Start Date | End Date | Assigned To | % Complete | Predecessors | Duration
UVA BME Masters in Engineering
| Masters in Engineering Academic Program |  | 2019-08-23 | 2020-12-21 |  | 25% |  | 347d
| BME 6550 - Clinical Applications of Biomedical Technologies |  | 2019-08-23 | 2019-12-23 |  | 100% |  | 87d
| BME 6060 - Biomedical Innovation |  | 2020-01-13 | 2020-05-08 |  |  |  | 85d
| Data Science Intensive |  | 2020-07-13 | 2020-07-17 |  |  |  | 5d
| Biomedical Design Principles |  | 2020-07-20 | 2020-08-07 |  |  |  | 15d
| BME 8995 - Masters Research |  | 2020-08-28 | 2020-12-22 |  |  |  | 83d
| Biomedical Career Pathways |  | 2020-08-28 | 2020-12-22 |  |  |  | 83d
| Module I - Observing the Continuum |  | 2019-08-23 | 2020-01-13 |  | 89% |  | 102d
TRUE | Pre-Observation Clearance |  | 2019-08-23 | 2019-09-25 |  | 100% |  | 24d
| HIPAA Training | Complete | 2019-08-23 | 2019-09-04 |  | 100% |  | 9d
| Inoculations | Complete | 2019-08-23 | 2019-09-09 |  | 100% |  | 12d
| Documentation | Complete | 2019-08-23 | 2019-09-25 |  | 100% |  | 24d
| Team Assignments | Complete | 2019-09-04 | 2019-09-04 |  | 100% |  | 1d
| Renal Care | Complete | 2019-09-04 | 2019-09-04 |  | 100% |  | 1d
| Pediatric Cardiac Care | Complete | 2019-09-04 | 2019-09-04 |  | 100% |  | 1d
| Adult Cardio Care | Complete | 2019-09-04 | 2019-09-04 |  | 100% |  | 1d
| Adult Neuro Care | Complete | 2019-09-04 | 2019-09-04 |  | 100% |  | 1d
| Clinical Observations - Phase I | Complete | 2019-09-11 | 2019-12-31 |  | 100% |  | 80d
| Clinical Observation Logs | Complete | 2019-09-11 | 2019-12-23 |  | 100% |  | 74d
TRUE | Class Presentation | Complete | 2019-10-23 | 2019-11-18 |  | 100% |  | 19d
| Ped. Cardiac Team | Complete | 2019-10-23 | 2019-10-23 |  | 100% |  | 1d
| Renal Team | Complete | 2019-10-30 | 2019-10-30 |  | 100% |  | 1d
| Adult Neuro Team | Complete | 2019-11-06 | 2019-11-06 |  | 100% |  | 1d
| Adult Cardio Team | Complete | 2019-11-18 | 2019-11-18 |  | 100% |  | 1d
TRUE | Review Clinical Logs | Complete | 2019-12-21 | 2019-12-31 |  | 100% |  | 8d
| Clinical Challenge Selection | In Progress | 2019-11-13 | 2020-01-13 |  | 58% |  | 44d
TRUE | Identify 25 Candidates | Complete | 2019-11-13 | 2019-11-20 |  | 100% |  | 6d
| Select 3 Finalists | Complete | 2019-11-20 | 2019-12-04 |  | 100% |  | 11d
| Make Final Decision | Complete | 2019-12-04 | 2020-01-13 |  | 75% |  | 29d
TRUE | Execute "Contract" | In Progress | 2019-12-04 | 2020-01-13 |  | 25% |  | 29d
TRUE | Problem Statement | In Progress | 2019-12-04 | 2020-01-13 |  | 50% |  | 29d
TRUE | Research Paper | Complete | 2019-11-06 | 2019-11-27 |  | 100% |  | 16d
| Module II - Masters Project Planning |  | 2020-01-14 | 2020-04-21 |  | 0% |  | 71d
TRUE | Problem Statement Presentations | Not Started | 2020-01-14 | 2020-01-14 |  | 0% |  | 1d
| Advanced Literature Research | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Anatomy | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Physiology | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Pathology | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Current Standard of Care | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Patents | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Current product offerings | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
| Current Clinical Practice | Not Started | 2020-01-14 | 2020-01-28 |  | 0% |  | 11d
TRUE | Extended Citation Bibliography Due | Not Started | 2020-01-28 | 2020-01-28 |  | 0% |  | 1d
| Published Data and Analytics | Not Started | 2020-01-14 | 2020-02-04 |  | 0% |  | 16d
| Incidence, prevalence, and trends | Not Started | 2020-01-14 | 2020-02-04 |  | 0% |  | 16d
| Demographics | Not Started | 2020-01-14 | 2020-02-04 |  | 0% |  | 16d
TRUE | Analytics Paper Due | Not Started | 2020-02-04 | 2020-02-04 |  | 0% |  | 1d
| UVA Clinical Data Records | Not Started | 2020-01-28 | 2020-03-03 |  | 0% |  | 26d
| CDR Training and Authorization | Not Started | 2020-01-28 | 2020-03-03 |  | 0% |  | 26d
TRUE | UVA Data Analytics Paper | Not Started | 2020-03-03 | 2020-03-03 |  | 0% |  | 1d
| Advanced Project Planning | Not Started | 2020-04-15 | 2020-04-15 |  | 0% |  | 1d
TRUE | Research Plan Due | Not Started | 2020-04-15 | 2020-04-15 |  | 0% |  | 1d
TRUE | Estimated Budget Due | Not Started | 2020-04-15 | 2020-04-15 |  | 0% |  | 1d
TRUE | Data Analytics Project Plan Due | Not Started | 2020-04-15 | 2020-04-15 |  | 0% |  | 1d
| Verification and Concept Viability | Not Started | 2020-02-18 | 2020-04-21 |  | 0% |  | 46d
| Design Critical Test Hypothesis | Not Started | 2020-02-18 | 2020-02-25 |  | 0% |  | 6d
| Component Fabrication | Not Started | 2020-02-25 | 2020-03-17 |  | 0% |  | 16d
| Test Fixtures and Test Resources | Not Started | 2020-02-25 | 2020-03-17 |  | 0% |  | 16d
| Conduct Verification Studies | Not Started | 2020-03-17 | 2020-04-21 |  | 0% |  | 26d
TRUE | Final Report on Concept Viability | Not Started | 2020-04-28 | 2020-04-28 |  | 0% |  | 1d
| Module III - Technology Development |  | 2020-01-21 | 2020-04-28 |  | 0 |  | 71d
| Design Controls | Not Started | 2020-01-21 | 2020-01-21 | Jonathan Rosen | 0% |  | 1d
| Cville BioHub | Not Started | 2020-01-27 | 2020-01-27 | Nikki Hastings | 0% |  | 1d
| Intro to Design Principles | Not Started | 2020-01-28 | 2020-02-03 | Anselmo Canfora | 0% |  | 5d
| Case Study 1 | Not Started | 2020-01-28 | 2020-02-03 |  | 0% |  | 5d
| Data Science Tools and Applications | Not Started | 2020-02-04 | 2020-02-10 | Jody Reyes | 0% |  | 5d
| Case Study 2 | Not Started | 2020-02-04 | 2020-02-10 |  | 0% |  | 5d
| Human Factors and Mnfg Design | Not Started | 2020-02-11 | 2020-02-17 | Sean Higgins | 0% |  | 5d
| Case Study 3 | Not Started | 2020-02-11 | 2020-02-17 |  | 0% |  | 5d
| Verification and Validation Testing | Not Started | 2020-02-18 | 2020-02-24 | Jonathan Rosen | 0% |  | 5d
| Case Study 4 | Not Started | 2020-02-18 | 2020-02-24 |  | 0% |  | 5d
| Visualizing your Design Concepts | Not Started | 2020-02-25 | 2020-03-02 |  | 0% |  | 5d
| Case Study 5 | Not Started | 2020-02-25 | 2020-03-02 |  | 0% |  | 5d
TRUE | Critical Experiment Design Presentations (20 min) | Not Started | 2020-03-03 | 2020-03-03 |  | 0% |  | 1d
TRUE | Project Update Presentations (5 min) | Not Started | 2020-03-16 | 2020-03-16 |  | 0% |  | 1d
| Risk Management and Mitigation | Not Started | 2020-03-17 | 2020-03-23 | Jonathan Rosen | 0% |  | 5d
| Case Study 6 | Not Started | 2020-03-17 | 2020-03-23 |  | 0% |  | 5d
| Regulatory Pathways | Not Started | 2020-03-24 | 2020-03-30 | TBD | 0% |  | 5d
| Case Study 7 | Not Started | 2020-03-24 | 2020-03-30 |  | 0% |  | 5d
| IP Strategies | Not Started | 2020-03-31 | 2020-04-06 | Jason Bernstein | 0% |  | 5d
| Case Study 8 | Not Started | 2020-03-31 | 2020-04-06 |  | 0% |  | 5d
| Reimbursement Realities | Not Started | 2020-04-07 | 2020-04-07 | TBD | 0% |  | 1d
| Packaging and Sterilization | Not Started | 2020-04-13 | 2020-04-13 | TBD | 0% |  | 1d
| Intro to Commercialization Strategies | Not Started | 2020-04-14 | 2020-04-14 | Jonathan Rosen | 0% |  | 1d
| Business Model Canvas | Not Started | 2020-04-20 | 2020-04-20 | Jonathan Rosen | 0% |  | 1d
TRUE | Final Presentation on Concept Viability | Not Started | 2020-04-28 | 2020-04-28 |  | 0% |  | 1d
Module IV - Design Principles
| Data Science Intensive |  | 2020-07-13 | 2020-07-17 |  |  |  | 5d
| Data Science Bootcamp |  | 2020-07-13 | 2020-07-16 |  |  |  | 4d
| BME Data Applications |  | 2020-07-16 | 2020-07-17 |  |  |  | 2d
| Biomedical Design Principles |  | 2020-07-20 | 2020-08-07 |  |  |  | 15d
| SARC Intensive |  | 2020-07-20 | 2020-07-31 |  |  |  | 10d
| BME Design Workshop |  | 2020-08-03 | 2020-08-07 |  |  |  | 5d
Module V - Technology Validation
| Clinical Studies - Phase II |  | 2020-01-13 | 2020-12-21 |  |  |  | 246d
| Build "Is Like" Prototype System |  | 2020-08-28 | 2020-12-14 |  |  |  | 77d
| Assemble Masters Project "Binder" |  | 2020-01-14 | 2020-12-14 |  |  |  | 240d
TRUE | Final Presentations (60 min) |  | 2020-12-14 | 2020-12-18 |  |  |  | 5d
Receive BME Masters Degree
TRUE | UVA Commencement! |  | 2020-12-21 | 2020-12-21 |  |  |  | 1d

## 6060 Deliverables
Module II - Masters Project Planning |  | 2020-01-14 | 2020-04-21 | 71d
Problem Statement Presentations | Completed | 2020-01-14 | 2020-01-14 | 1d
Advanced Literature Research | Started | 2020-01-14 | 2020-01-28 | 11d
Anatomy | Not Started | 2020-01-14 | 2020-01-28 | 11d
Physiology | Not Started | 2020-01-14 | 2020-01-28 | 11d
Pathology | Not Started | 2020-01-14 | 2020-01-28 | 11d
Current Standard of Care | Not Started | 2020-01-14 | 2020-01-28 | 11d
Patents | Not Started | 2020-01-14 | 2020-01-28 | 11d
Current product offerings | Not Started | 2020-01-14 | 2020-01-28 | 11d
Current Clinical Practice | Not Started | 2020-01-14 | 2020-01-28 | 11d
Revised Problem Statement Presentations | Not Started | 2020-01-21 | 2020-01-21 | 1d
Extended Citation Bibliography Due | Not Started | 2020-01-28 | 2020-01-28 | 1d
Published Data and Analytics | Not Started | 2020-01-14 | 2020-02-04 | 16d
Incidence, prevalence, and trends | Not Started | 2020-01-14 | 2020-02-04 | 16d
Demographics | Not Started | 2020-01-14 | 2020-02-04 | 16d
Analytics Paper Due | Not Started | 2020-02-04 | 2020-02-04 | 1d
UVA Clinical Data Records | Not Started | 2020-01-28 | 2020-03-03 | 26d
CDR Training and Authorization | Not Started | 2020-01-28 | 2020-03-03 | 26d
UVA Data Analytics Paper | Not Started | 2020-03-03 | 2020-03-03 | 1d
Advanced Project Planning | Not Started | 2020-04-15 | 2020-04-15 | 1d
Research Plan Due | Not Started | 2020-04-15 | 2020-04-15 | 1d
Estimated Budget Due | Not Started | 2020-04-15 | 2020-04-15 | 1d
Data Analytics Project Plan Due | Not Started | 2020-04-15 | 2020-04-15 | 1d
Verification and Concept Viability | Not Started | 2020-02-18 | 2020-04-21 | 46d
Design Critical Test Hypothesis | Not Started | 2020-02-18 | 2020-02-25 | 6d
Component Fabrication | Not Started | 2020-02-25 | 2020-03-17 | 16d
Test Fixtures and Test Resources | Not Started | 2020-02-25 | 2020-03-17 | 16d
Conduct Verification Studies | Not Started | 2020-03-17 | 2020-04-21 | 26d
Final Report on Concept Viability | Not Started | 2020-04-28 | 2020-04-28 | 1d

## 6060 Schedule
Week | Session | Module III - Technology Development | 2020-01-21 | 2020-04-28 | Schedule
1 | 1 | Program and Course Overview | 2020-01-13 |  | Jonathan Rosen
| 2 | Problem Statement Presentations |  | 2020-01-14 | Teams
2 | 3 | Design Controls/Revised Problem Statement | 2020-01-21 | 2020-01-21 | Jonathan Rosen/Teams
| 4 | Cville BioHub | 2020-01-27 |  | Nikki Hastings
3 | 5 | Intro to Design Principles | 2020-01-28 |  | Anselmo Canfora
| 6 | Case Study 1 |  | 2020-02-03 | Hill Johnson
4 | 7 | Data Science Tools and Applications | 2020-02-04 |  | Jody Reyes
| 8 | Case Study 2 |  | 2020-02-10 | Robin Liu
5 | 9 | Human Factors and Mnfg Design | 2020-02-11 |  | Sean Higgins
| 10 | Case Study 3 |  | 2020-02-17 | Jordan Word
6 | 11 | Verification and Validation Testing | 2020-02-18 |  | Jonathan Rosen
| 12 | Case Study 4 |  | 2020-02-24 | Tehan Dassanayaka
7 | 13 | Visualizing your Design Concepts | 2020-02-25 |  | Ty Hagler & Andrew DiMeo
| 14 | Case Study 5 |  | 2020-03-02 | Jay Hanckel
8 | 15 | Critical Experiment Design Presentations (20 min) |  | 2020-03-03 | Teams
| 16 | Project Update Presentations (5 min) |  | 2020-03-16 | Teams
9 | 17 | Risk Management and Mitigation | 2020-03-17 |  | Jonathan Rosen
| 18 | Case Study 6 |  | 2020-03-23 | Angie Campo
10 | 19 | Regulatory Pathways | 2020-03-24 |  | TBD
| 20 | Case Study 7 |  | 2020-03-30 | James Bonafini
11 | 21 | IP Strategies | 2020-03-31 |  | Jason Bernstein
| 22 | Case Study 8 |  | 2020-04-06 | Lisa Chen
12 | 23 | Reimbursement Realities | 2020-04-07 |  | Tyrone
| 24 | Packaging and Sterilization | 2020-04-13 |  | TBD
13 | 25 | Intro to Commercialization Strategies | 2020-04-14 |  | Jonathan Rosen
| 26 | Business Model Canvas | 2020-04-20 |  | Jonathan Rosen
14 | 27 | Final Presentation on Concept Viability |  | 2020-04-28 | Teams